## REQUIREMENT MATRIX
REQUIREMENTS TRACEABILITY MATRIX
PROJECT MANAGER: |  |  |  | PROJECT ID: |  | AQ-CMS-01
PROJECT SPONSOR: |  |  |  | PROJECT TITLE: |  | AGHAMazing Quest CMS
REQUIREMENT INFORMATION | [5 empty] | RELATIONSHIP TRACEABILITY
ID | CATEGORY | REQUIREMENT | PRIORITY | SOURCE | TRACEABILITY ID | BUSINESS OBJECTIVE | DELIVERABLE(S) | VERFICATION | VALIDATION | TEST CASE ID
REQ-001 | Mandatory | Role-based access control with specific permissions for Encoder, Reviewer, and Approver roles. | High | Stakeholder Interviews, Final Paper | 1 | Achieve 100% role-based access control | RBAC System | System enforces role permissions according to workflow; unauthorized actions are blocked. | Staff can perform only allowed functions based on their role. | TC1.1.1, TC1.1.2, TC1.1.3, TC1.3.4, TC1.5.4, TC1.7.4
REQ-002 | Mandatory | Content workflow management system supporting draft, review, approve, publish, and archive stages. | High | Use Cases UC2.2, UC2.3, UC2.4 | 2 | Streamline content approval process | Content Workflow Engine | Content moves through workflow stages according to permissions; status changes are logged. | Content approval time reduced by 60% compared to current process. | TC2.2.1, TC2.3.1, TC2.3.2, TC2.3.3, TC2.4.1
REQ-003 | Mandatory | Content versioning system to track changes and enable reverting to previous versions. | High | Use Case UC2.5, Test Cases TC2.5.1-TC2.5.4 | 3 | Ensure content accuracy and quality control | Version History Module | Users can view chronological version history, compare differences between versions, and restore previous versions. | Content errors can be corrected within minutes without developer assistance. | TC2.5.1, TC2.5.2, TC2.5.3, TC2.5.4
REQ-004 | Mandatory | Secure authentication system with password complexity requirements. | High | Test Case TC1.2.5, Final Paper (Security section) | 4 | Meet security compliance standards | Authentication Module | System enforces password requirements (minimum 8 characters with mix of letters and numbers); authentication failures are logged. | 100% of staff accounts comply with password policies. | TC1.1.1, TC1.1.2, TC1.1.3, TC1.2.5
REQ-005 | Mandatory | Audit logging system to record all user activities and system changes. | High | Test Cases TC1.3.5, TC1.5.5, TC1.6.5, TC1.7.6, TC1.8.6 | 5 | Ensure accountability and traceability | Audit Logging Module | System logs all critical actions (user management, role changes, content modifications) with timestamps, user IDs, and action details. | Full audit trail available for compliance and troubleshooting. | TC1.3.5, TC1.5.5, TC1.6.5, TC1.7.6, TC1.8.6
REQ-006 | Mandatory | RESTful API integration between CMS and mobile application for content synchronization. | High | Project Scope, Technology Stack document | 6 | Enable seamless content delivery | API Integration Layer | Content updates in CMS immediately available to mobile app through API endpoints. | Content updates appear in mobile app within minutes of publishing. | Not yet covered in test cases
REQ-007 | Mandatory | Content upload and management system supporting various file types (images, audio, documents). | High | Use Case UC2.1 | 7 | Enable independent content management | Media Management Module | System accepts and processes various file types; duplicates are prevented; metadata is stored. | Staff can upload, organize, and manage content without developer assistance. | TC2.1.1, TC2.1.2, TC2.1.3
REQ-008 | Should have | Analytics reporting on content usage and user engagement. | Medium | Project Scope, Test Cases TC3.1.1-TC3.1.4 | 8 | Provide data for content improvement decisions | Analytics Dashboard | System generates reports on user engagement with metrics and visualizations; reports can be downloaded. | Content strategy decisions informed by analytics data. | TC3.1.1, TC3.1.2, TC3.1.3, TC3.1.4
REQ-009 | Should have | Notification system to alert users about pending actions (approvals, rejections). | Medium | Use Case UC2.3 (mentions notifications) | 9 | Improve workflow efficiency | Notification Engine | System sends notifications when content requires attention; users can filter notifications by priority. | Average content approval time reduced by 40%. | Not yet covered in test cases – Ongoing
REQ-010 | Should have | Content search and filtering capabilities. | Medium | Project Scope (Search & Indexing) | 10 | Enable efficient content discovery | Search Module | Users can search content by title, description, date, and status; results display within 2 seconds. | Staff spend less time locating specific content items. | Partially covered in TC2.5.4

## DEFINITIONS
DEFINITIONS
PROJECT MANAGER
The person with responsbility for managing and delivering the project. They will own this log, but may not be the person maintaining it.
PROJECT ID
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
PROJECT SPONSOR
The person with ultimate accountablity for the project. They will hold the purse strings.
PROJECT TITLE
The name of the project, this should align with the name given on other project documents (rather than being a nickname).
REQUIREMENT ID
Give each requirement a unique identifier or reference so that it can be easily traced throughout the project life-cycle.
CATEGORY
Provide a category for the requirement typical categories are: functional, non-functional, usability, security, performance, maintainability etc.
REQUIREMENT
Describe the requirement that needs to be met by the project. The requirement might be a product, some product functionality, a service, or a result.
PRIORITY
Provide a priority for the requirement. For example, mandatory, should have, nice to have or high, medium, low.
SOURCE
Enter the name of the stakeholder that identified the requirement.
BUSINESS OBJECTIVE
Document the business objective that this requirement will meet or help to meet. The business objective will come from the project charter or the Project business Case.
DELIVERABLE(S)
List the deliverable or deliverables that will make up this requirement.
TRACEBILITY ID
The identifier that relates the validation and verification to the requirements.
VERIFICATION
Explain how you will test that the requirement is completed satisfactorily. For example 99.9% uptime for user acceptance of software.
VALIDATION
Explain how the requirement will be validated or tested. This will often be via user acceptance testing, but it might also be by the achievement of a milestone or perhaps by the completion of a key performance indicator.
TEST CASE ID
A Test Case identifier is referenced by the test design specification and the test procedure specifications. which identify a test case uniquely.

## CUSTOMISE
HOW TO CHANGE THE MENU ITEMS IN STATUS FIELDS
Default settings
We have not set any drop down menus, as it is likely that most projects will have different priorities and categories.
How to create a drop down menu
Click on Data tab > Data Validation > Settings > List
In the Source field enter the menu items separated by a comma.
To change the menu items
To change the menu options or remove the dropdown select Data > Data Validation > Settings > List
ADDITIONAL FIELDS YOU MIGHT WANT TO ADD
Supplier - On projects with multiple suppliers you may want to add a field to note the supplier responsible.
WBS ID - Add WBS ID so that the requirement can be linked to the Work Breakdown Structure and project schedule.
Test case ID - Later in the project you may want to link the requirement to the test cases that will be used to
check that the requirement meets the business objective.